# CURRENT  CONSTRUCTION ACTIVITIES

## LAST WEEK - WEEK ENDING 03/15/2025

3rd Floor:

- Furniture Install

- Punch List Work

2nd Floor:

- RTCC Equipment & Furniture Install

- Punch List Work

1st Floor:

- Terminating data Cables at IT Closets

- Testing 1st Floor Data Cables

- Access Control Devices

- Teller Speakers & Glass

- Rubber Base

- Signage

- Furniture

- TV’s

- Touch Up Paint

Basement:

- Millwork

- Water Dinking Fountains

- Final Paint

- Flooring

Exterior:

- Planting

- Crack & Fill at Upper Lot

THIS WEEK – WEEK ENDING 03/22/2025

3rd Floor:

- Routing Data at Furniture

- Punch List Work

2nd Floor:

- Routing Data at Furniture

- Punch List Work

1st Floor:

- Terminating Data Cables at IT Closets

- Testing 1st Floor Data Cables

- Signage

- Audio Visual

- Furniture

Basement:

- Terminating Data Cables at IT Closets

- Millwork

- Final Paint

- Flooring

- Existing Elevator Inspection

- New Elevator Adjusting

- Furniture

Exterior:

- Crack & Fill at Upper Lot

- Pressure Washing Brick

- Fencing

# JOBSITE PHOTOS

Service & Teller Windows

Data Terminations at IT Closet

Painting Exterior Railings

Floor Prep & Install at Gym

WEATHER

### Weather delays this week: 0

- Total Weather Delays: 55

SAFETY REPORT

## Days without an accident: 410

  - Days without lost time: 410

MILESTONE TRACKING

    - Construction Start: August 21, 2023

    - Current Contract Completion Date: Mar 14, 2025